## Step1-Overview
Here we list down the various Epics that define the product to be made. Make sure there are enough Epics to give a comprehensive idea of what is required to achieve your product.
Epic
Game State Management
Audio
Graphics
Map Design
Recipe System
Ingredient System
Scoring System
Timer System
Cooking logic
Level Design
UI
Player
Collision
Enemy

## Step2-Task Backlog
| Priority | Task | Description | Hours Estimate | Week | Assignee | Type | Completed?
Player | Must Have | Player movement | Player Movement - keys 'W','A', 'S' , 'D' (up,left,down, right) | 1 | 3 | Elvis | Code | Yes
Ingredient System | Must Have | Randomize Ingredients | Randomizing box content after each pick up - rand() and srand() std::m19937 rng(rd()); std::uniform_int_distribution<int> | 4 | 4 | Elvis | Code | Yes
Map Design | Must Have | Collision Detection | Boundaries detection for interactive objects in the game - cooking station - ingredients station - dustbin | 2 | 4 | Elvis | Code | Yes
Player | Should Have | Dash Mechanic | Dash movement when press shift with a cooldown | 2 | 6 | Elvis | Code | Yes
Player | Should Have | repellent | repellent for the player to hold and spot where player can put back the repellent | 2 | 7 | Elvis | Code | Yes
Player | Must Have | shoot with repellent | Allow players to interact with mice to prevent them from stealing ingredients with some kind mouse repellent and shoot it toward the mouse direction to chase away the mice.where players can press a key (e.g., ‘Spacebar’) near a mouse to scare it away | 3 | 7 | Elvis | Code | Yes
UI | Must Have | Main Menu Page | Main menu. Start Game Option Quit Game Option & confirmation prompt How To Play Credits | 3 | 8 | Elvis | Art | Yes
| Must Have | Intro Screen Bypass | Intro screens must be able to be bypassed with a single mouse-click (left and right), key-press (Enter, spacebar, and Escape), AND button-press (Start and A, if gamepads are supported). You do not have to skip with a mouse click if the game does not use the mouse and the cursor is invisible.) NOTE: This single piece of input may bypass all remaining intro screens or only one at a time. NOTE: If a player attempts to bypass the intro screens, it is fine to skip the DigiPen logo. | 1 | 8 | Elvis | Code | Yes
Graphics | Must Have | credits | Credit scene available with things like who we working with and credit to the school and proffessor | 2 | 10 | Elvis | Code | Yes
Graphics | Must Have | DigiPen Logo | Game must display the official DigiPen logo all by itself as the first screen upon launching. It must be displayed unaltered for at least 2 seconds, after which you can move on or start modifying the logo in an artistic way. This logo is located on GameCentralSG on Moodle. | 1 | 9 | Elvis | Code | Yes
Here we list down all the tasks required to achieve our goal for the project. Use the Epics listed in Step1-Overview to come up with these tasks. All Epics should have tasks listed to achieve that Epic. Rank each task with a Priority. Each "Must Have" task needs to be assgined to someone for completion. Add names in the table of Step3-Budgeting and the assignee column will have a dropdown list for you to pick from. "Week" refers to the week the task should be started and finished. Estimate the number of hours the task might require and always set which week this task is to be completed by. Everyone can only commit a certain number of hours each week. Make sure that the total time for all tasks in a week does not exceed that commitment. When a task is completed, the Hours Estimate will be interpreted as the time taken to actually finish the task. If a task does not belong to any Epic, leave that part empty for that task.
Instructions
Cooking logic | Must Have | Wok array | Combining Ingredient at wok (cooking station) - function taking in 1 to 3 ingredients max into an empty array | 4 | 3 | Kerrin | Code | Yes
Ingredient System | Must Have | Ingredient array | Ingredient Storage box - each box is holding 1 ingredient 6 Ingredients (array, each element is holding 1 ingredient) | 3 | 4 | Justin | Code | Yes
Map Design | Must Have | Collision Detection | Collision for the objects in the environment : ( player cannot walk through the objects on the map (like wok, dustbin,ingredient storage area) | 4 | 4 | Justin | Code | Yes
UI | Must Have | Pause page | R key = Pause menu with an option to exit the game. "Quit Game" button on the Pause menu. | 1 | 5 | Justin | Code | Yes
Enemy | Must Have | Mice mechanic | Program the movement patterns for mice, including random roaming and targeted movement toward ingredients. Implement an ingredient detection system where mice can identify ingredients within a set radius and move towards them. Add logic for the mice to pick up an ingredient and disappear after a short time. | 4 | 9 | Justin | Code | Yes
Enemy | Could Have | Mice mechanic | Create and implement animations for mice, including idle movement and 4 directions | 2 | 9 | Justin | Code | Yes
Enemy | Could Have | Mice mechanic | Add visual cues (e.g., mouse squeaking and animations) to alert players when mice are targeting an ingredient. | 2 | 9 | Justin | Code | Yes
Player | Could Have | Player Speed Boost | Power up for the player to pick up to become faster | 4 | 10 | Justin | Code | No
Audio | Could Have | Sound Effects | Sound effects when cooking | 2 | 10 | Kerrin | Audio | Yes
Audio | Should Have | Sound Effects | Background music for the game | 3 | 10 | Justin | Audio | Yes
Cooking logic | Could Have | stove | stove geting having a 30% change of getting dirty | 3 | 2 | Kerrin | Code | Yes
Cooking logic | Must Have | Start cooking button | Activating the stove to cook (Button to prompt the player to start the cooking process) will only show when there is 2 or more ingredients in the wok | 2 | 3 | Kerrin | Code | Yes
Ingredient System | Must Have | Clear | Dustbin to get rid of the ingredients | 2 | 3 | Kerrin | Code | Yes
Scoring System | Must Have | Score Display | Score display - (Condition check : if the items served after the cooking is done is the same as the recipe the player will earn 5points. else the player will lose 2points ) | 4 | 5 | Kerrin | Code | Yes
Scoring System | Must Have | Win | Win page: if the player accumulated points is more then 0 the player wins Restart Game Option Return to Main Menu Option Quit Game Option | 3 | 5 | Kerrin | Code | Yes
Scoring System | Must Have | Lose | Lose page : Restart Game Option Return to Main Menu Option Quit Game Option | 1 | 6 | Kerrin | Code | Yes
UI | Should Have | Design and UI Implementation | Design and UI (area) | 3 | 7 | Kerrin | Art | Yes
UI | Should Have | Design and UI Implementation | Create sprites for stove, ingredient box, recipes and player | 4 | 7 | Kerrin | Art | Yes
Graphics | Must Have | Window Title | Window title must reflect the name of the game in English characters. | 1 | 7 | Kerrin | Code | Yes
Graphics | Could Have | Dynamic Cooking Area Movement | Cooking area moves every ten seconds | 6 | 8 | Kerrin | Code | No
UI | Must Have | Implementing assets | Implement all UI assets into the game | 2 | 8 | Kerrin | Code | Yes
UI | Should Have | Design and UI Implementation | Create game logo | 1 | 10 | Kerrin | Art | Yes
Player | Must Have | Player movement | Player Movement - Picking up & putting the ingredient key 'E' ( pressing once to pick up an ingredient if hand is empty, again to drop the item ) | 2 | 3 | Norman | Code | Yes
Recipe System | Must Have | Recipe System | Recipe research | 1 | 3 | Norman | Admin | Yes
Recipe System | Must Have | Recipe Display | Show recipes (timer : 10 sec. when the timer runs out the recipe changes to the next receie that is randomly pulled from the array of recipes | 3 | 4 | Norman | Code | Yes
Recipe System | Must Have | Recipe Display | Show recipes ( stored in array ; the different 6 recipies stored in each array recepie) | 3 | 4 | Norman | Code | Yes
Timer System | Must Have | Timer | Timer ( 2sec for 2 ingredients, 5 sec for 3 ingredients) the timer will start to countdown after the Start to cook button (task 11) has been triggered | 2 | 4 | Norman | Code | Yes
Level Design | Must Have | Mini game | QTE gauge during cooking, when player activates the cooking station, QTE gauge activates Player has to successfully complete it or the stove will not start cooking and all ingredients in the stove disappear | 6 | 6 | Norman | Code | Yes
Recipe System | Could Have | Progressive Recipe Complexity | Recipe get longer as level progresses | 2 | 6 | Norman | Code | No
Level Design | Must Have | Implementing animations | Implement all animations for player and mouse into the game | 4 | 8 | Norman |  | Yes
Player | Could Have | cleaning | by pressing c on the stove the player will clean the stove for 4 seconds | 2 | 9 | Norman | Code | Yes
UI | Must Have | Tutorial | Introduction page (teach the player how to play) | 2 | 10 | Norman | Art | Yes

## Step3-Budgeting
Instructions
Here all members of the team declare their commitments to the project and check if the delegated workload is within what has been committed. At least 50% of the Planned Load needs to be Code tasks. If the given excel sheet formula does not auto-fill the hours from the Backlog correctly, students are to fill it in manually.
"Weekly Commitment" | Each student needs to declare the number of hours per week that they will work on the project. Every student has their own degree of ability to cope with this class and the other classes. An honest and realistic answer to this needs to be set, to better control the scope of the project and by extension, the scope of work needed to be done per individual.
"Total Commitment" | The product of Weekly Commitment and the number of weeks committed to working on this project. This will represent the total amount of work that can be done by the individual.
"Planned Load" | Total workload assigned to this individual. Only counting tasks that are Must Have. These should not exceed the total number hours stated in Total Commitment. There is an excel formula in that slot. Regardless if the formula works, the number in the cell must be reported correctly.
"Code Load" | Code Load should be more than or equal to half of the Planned Load. This is a class for Computer Science students, everyone needs to do that minimal amount of Code.
Student Name | Student DigiPen e-mail | Weekly Commitment | Total Commitment | Planned Load (Must haves) | Planned Code Load (Must haves) | Completed Load | Completed Code Load
Elvis | elvisshengjie.lim@digipen.edu | 10 | 90 | 17 | 14 | 21 | 18
Kerrin | kerrinlemin.k@digipen.edu | 10 | 90 | 19 | 19 | 32 | 22
Justin | yimo.kong@digipen.edu | 10 | 90 | 12 | 12 | 19 | 16
Norman | chan.f@digipen.edu | 10 | 90 | 23 | 16 | 25 | 18
| Team Totals | 40 | 360 | 71 | 61 | 97 | 74

## TaskTypes
Task Types | Description & Requirements | Requirements
Level | For tasks related to creating levels for the project. Ideally done without hardcoding all objects in the level within code. | @Must have a beginning and an end @Meaningful choices for the player to make @Clear objective
Art | For tasks related to creating visual art assets for the project. This includes fonts. Fonts : There are some license free fonts allowed for use. Refer to forum post. This should be kept to a minimum for RTIS and IMGD students. | @Refer to the EULA that you signed at the start of the semester @Do not use existing art assets even if they are "license free" @Tools used in the generation of art assets must be license and cost free
Audio | For tasks related to finding, creating and/or getting audio assets into the project. There are audio assets provided by the school via MetaDigger. Refer to forum post. The tasks related to coding an audio system to play audio assets should be under "Code". The audio system is a coded feature. | @Refer to the EULA that you signed at the start of the semester @Usage of existing audio assets allowed only for those found in the school's MetaDigger @Do not use external existing audio assets even if they are "license free", provided for or generated by tools @Recording your own audio, editting it with a free tool and using that asset is allowed
Code | For tasks related to feature implementation and code integration. Hardcoding levels and content for the game does not fall under this category. That would be under the task type of "Level" | @Feature functions as described and intended @No crashes, warnings, errors from implementation @Does not break existing features. If it does, those breaks should be fixed for this task to be done
Bug Fix | For tasks related to fixing bugs that have been detected. Debugging is expected to be done during coding and development, but not all bugs would get detected during that phase. | @Symptoms identified with bugs gone @No crashes, warnings, errors from implementation @Does not break existing features. If it does, those breaks should be fixed for this task to be done
Admin | For administrative tasks like: @Team Meetings @Presentation materials @Production documents @Marketing materials

## Priorities
Priorities | Brief | Completion
Must Have | Critical, cannot do without | Yes
Should Have | Important to the project but not vital | No
Could Have | Nice to have
Won't Have | Would not contribute to your project, can do without

## Plan Grading (Week 2)
Plan Grading (Week 2)
Teams start with an "A" grade. Accumulated penalties will be applied to lower the grade. Teams do not need to fill this page. This page is only relevant for the very first plan submission. This page will be used only for grading the Week 2 submission.
Penalties | Penalty Range | Penalty Given | Feedback
Step 2 "Week" not filled with the relevant week numbers. | -1 per offending task
Assigned tasks leads to member/s exceeding their time budget. Example. Assignee commits 10 hours a week for 6 weeks. 61 hours of work were assigned. Penalty given. | -2 per offending member
Tasks are too vague. Tasks title and/or description does not sufficiently inform the assignee the scope of work required and/or begin work. | -1 per 10% of tasks
Tasks too large. Requires more than a week of the assignee's commitment. Break it down into smaller tasks. Should a task require more than a week of work, a team can be set back significantly if that task is not completed by the allocated date. Penalty is high to discourage this. | -1 per offending task
Missing data on any of the Step pages. | -1 per missing data field. A data field here is defined as a single excel cell.
Too little coding. Includes but not limited to: - Member/s with less than 50% of work allocated in code - Member/s not working on meaningful features (example, just coding up structures without functions or systems to use them) - No work allocated to member. | -1 to -4
Priorities and/or sequences of tasks work against the completion of the project. Includes but not limited to: - "Must Have" features left to the end of the production pipeline - Key features not labelled as "Must Have" - Tasks with pre-requisites are planned to be completed without the pre-requisites completed. | -1 to -4
| Total Penalty | 0
Final Grade

## Plan Grading (Week 5)
Plan Grading (Week 5)
Teams start with an "A" grade. Accumulated penalties will be applied to lower the grade. Teams do not need to fill this page. This page is only relevant for the very first plan submission. This page will only be used for Week 5 grading.
Penalties | Penalty Range | Penalty Given | Feedback
Step 2 "Week" not filled with the relevant week numbers. | -1 per offending task
Assigned tasks leads to member/s exceeding their time budget. Example. Assignee commits 10 hours a week for 6 weeks. 61 hours of work were assigned. Penalty given. | -2 per offending member
Tasks are too vague. Tasks title and/or description does not sufficiently inform the assignee the scope of work required and/or begin work. | -1 per 10% of tasks
Tasks too large. Requires more than a week of the assignee's commitment. Break it down into smaller tasks. Should a task require more than a week of work, a team can be set back significantly if that task is not completed by the allocated date. Penalty is high to discourage this. | -1 per offending task
Missing data on any of the Step pages. | -1 per missing data field. A data field here is defined as a single excel cell.
Too little coding. Includes but not limited to: - Member/s with less than 50% of work allocated in code - Member/s not working on meaningful features (example, just coding up structures without functions or systems to use them) - No work allocated to member. | -1 to -4
Priorities and/or sequences of tasks work against the completion of the project. Includes but not limited to: - "Must Have" features left to the end of the production pipeline - Key features not labelled as "Must Have" - Tasks with pre-requisites are planned to be completed without the pre-requisites completed. | -1 to -4
| Total Penalty | 0
Final Grade

## Work Done Grading
Work Done
Work done will be evaluated with reference to what was planned in the previous backlog submission and what was completed in the current submission. Plans can change to adapt to the progress of production. Some tasks might become obsolete, work might be transferred from one person to another due to new demands and revelation. However, everyone still needs to have done work they can claim credit for. It is an issue if anyone has tasks constantly cancelled or transferred to others. Work done will be considered during Week 5 and Week 12 submissions of the backlog. They will affect the First and Final milestone grade of an individual respectively.
Penalty | Penalty Range
Every 10% of allocated "Must Have" work not completed. This can be appealed if the team came into some consensus as to why certain tasks were cancelled, postponed or transferred to another etc. | -1 letter grade
No coding work done. | F grade